## Tracker
Date | Task# | Task | Sub-activity | Task-Progress if applicable | Hours invested
2020-01-25 | 0 | Learning Flask | Exploring Flask framework and how to construct application skeleton | 40% | 5
2020-01-26 | 1 |  |  |  | 8
2020-01-30 | 2 | Standalone Python script to read XML File, parse it and generate CSV | Exploring the lxml and xml python libraries | 50% | 3
2020-01-31 |  |  | Creating the modularized Python file with core functionality & docstrings | 50% | 3
2020-02-01 | 3 | Overall Flask application skeleton | Login Page + Home Page functionality | 40% | 10
2020-02-02 |  |  | Login Page + Home Page integration with Python standalone script Frontend aesthetic features (JS and CSS) | 60% | 12
2020-02-03 | 4 | Break | Break |  | 0
2020-02-04 | 5 | Pyspark tech requirements sync-up with Pooja | Connected with Pooja to understand Py-Spark config file requirements Devised strategy to print hierarchy of XML Tags in Jinja HTML |  | 2
2020-02-05 | 6 | Break | Break |  | 0
2020-02-06 | 7 | Create nested XML Tags as hierarchical Checkboxes | Began working on the FOR Loop to parse each array element into Jinja frontend. No concrete answer yet. | 5% | 2
2020-02-07 | 8 |  | Implemented the FOR Loop in Jinja, by incorporating highly intricate and inefficient sequence of IF-ELSE case statements and GLOBAL application variables. Need workaround. | 10% | 4
2020-02-08 | 9 |  | Implemented a custom tree data-structure by using wrapper function around the Python library Element. Managed to create parent-child link between tree-nodes. FOR/WHILE Loop limitation encountered again while trying to implement Depth First Traversal of nodes. Read up on how real-life product industry uses Flask, and why WHILE/FOR Loops aren't advisable for Jinja. Began working in Javascript, to parse the XML File. | 10% | 6
2020-02-09 | 10 |  | Successfully parsed the XML file using Javascript. Incorporated Depth First Traversal of nodes, and successfully generated a dynamic sequence of interlinked parent-child nodes. Nested hierarchy on selection generates array in Javascript. Managed to pass this array into server-side Python script and write into csv file. Need to implement similar logic for XSD but with more enhancements. | 40% | 9
2020-02-10 | 11 | Break | Awaiting confirmation from Atanu to proceed with Javascript code for XSD parsing. |  | 0
2020-02-11
2020-02-12
2020-02-13
2020-02-14
2020-02-15
2020-02-16
2020-02-17
2020-02-18